REQUEST Call FOR PROPOSAL- Mid-Term Evaluation for Collaboration across Societies for Peace, Inclusion, and Resilience (CASPIR) The Request for Proposal reference: BD-PS-RFP-1094 SUMMARY The Norwegian Refugee Council (NRC) is seeking an experienced & qualified person to assess the relevance, effectiveness, efficiency, and emerging outcomes of the project to date, and to provide recommendations for improved implementation and impact. Deadline for application is 8th Sep 2025 @ 16:00 (GMT +2) The consultant is/are envisaged to be contracted for the period of consultancy. PROCESS FOR APPLICATION We are opened to provide further information (background of the research, generic terms & conditions, information on award process) upon request. - Deadline for submission: 8th Sep 2025 @ 16:00 (GMT +2) Complete Proposal documents must be submitted by EMAILS Email for submission: SD.procurement@nrc.no CONTENT OF REQUEST FOR PROPOSAL - Terms of reference - How to Apply - Annex 1: Applicant checklist

Terms of Reference (ToR)

- Background

Context information

Sudan's prolonged crises, marked by civil unrest, intercommunal conflicts, and crimes against humanity, have led to widespread displacement and humanitarian challenges. Despite a 2020 peace agreement and the withdrawal of AU-UN forces, violence has escalated, worsened by deteriorating economic and political conditions. The conflict intensified on 15 April 2023 with clashes between the Sudanese Armed Forces (SAF) and the Rapid Support Forces (RSF) in Khartoum, spreading to Darfur and other regions, exacerbating the humanitarian situation. The current conflict has displaced over 3.6 million people across Sudan, adding to the pre-existing 3.8 million IDPs, predominantly in Darfur, requiring urgent assistance. The fighting has also driven over 1 million people to seek refuge in neighboring countries. Civilians, trapped and endangered by conflict, face obstacles fleeing violence, while humanitarian efforts are significantly hindered by security, logistical, and bureaucratic challenges.

The ongoing conflict in Sudan has affected the relatively stable White Nile and other states who are currently hosting high numbers of IDPs.

NRC’s overall country multi-year strategy (2022-2025) objective is to contribute to the survival, protection, dignity, and durable solutions for conflict- and displacement-affected people in Sudan. Its priorities are twofold - in the aftermath of violence and disaster, it provides immediate, emergency assistance. Where the effects of long-term displacement have taken hold, it contributes to minimizing the disadvantages of prolonged displacement by promoting durable solutions through impactful advocacy and effective, integrated programming. NRC Sudan focuses on five main result areas as part of its strategic response plan. These will ensure displacement-affected communities can access quality services and protection during the strategy period:

- Assist people to access and meet their basic needs and own priorities, especially in new emergency situations and in hard-to-reach areas;

- Protect people from armed conflict, abuse, and deprivation through evidence-based advocacy and policy analysis;

- Promote displaced people’s self-reliance and improve their path to durable solutions, including facilitation to voluntary and principled return solutions;

- Improve the quality of the broader humanitarian response, through i) augmenting coordination capacity (including improved field coordination), ii) strategic and local partnerships, and iii) promoting modern approaches, such as cash and market-based and digital technology-enabled approaches;

- Make significant efforts to ensure lessons learned and displacement-affected communities' priorities are shared across humanitarian actors.

- Background of the project

White Nile’s rural economy is primarily based on agriculture and livestock, similar to other farming–pastoralist regions. Across Sudan, these sectors account for about 20% of GDP and employ 65% of the population, with even higher reliance in rural states. Farming is mostly rain-fed (95%), leaving communities highly vulnerable to **erratic rainfall, floods, droughts, and other climate shocks**. Livestock herding—often nomadic—depends on natural grazing areas and seasonal water sources, creating potential for **resource-based conflicts** when grazing routes overlap with farmland or water points.

The economic crisis has sharply raised the cost of inputs like seeds, fodder, fertilizers, and equipment, making it harder for farmers and herders to sustain livelihoods. Climate change is intensifying risks, reducing yields (down 35% in 2021/22), and eroding resilience. Across rural Sudan—including White Nile—competition over land, water, and grazing areas is rising due to population growth, in-migration, and weak land governance. This often triggers disputes between pastoralists and farmers, worsened by lack of coordinated resource management and limited access to improved, climate-adapted farming techniques.

Women are central to agricultural labor and household resource management yet face barriers to land ownership and participation in decision-making. Their livelihoods are tied directly to land and natural resources, but traditional and systemic inequalities limit control over these assets.

With support from SIDA, NRC is implementing a project called Collaboration and Across Societies for Peace, Inclusion and Resilience. (CASPIR). This project seeks to enhance the climate resilience and economic stability of agro-pastoralist communities in White Nile State by addressing the intersecting challenges of environmental degradation, limited access to inputs and finance, and resource-based conflict.

The project aims to strengthen community capacity in managing land disputes and conserving the environment while boosting income and production. Using a conflict-sensitive approach, it will identify root causes of disputes and key actors in natural resource governance, then provide targeted training in collaborative dispute resolution, participatory planning, and improved agro-pastoralist techniques, alongside legal support and technical assistance. Community structures such as natural resource committees will be reinforced to promote equitable resource access. To improve livelihoods, the project will enhance inclusive access to land, rental markets, quality inputs, and credit, tailoring support for agro-pastoralists, community groups, and market actors.

The intervention focuses on improving livelihoods through the provision of climate-resilient agricultural inputs such as improved seeds, drought-tolerant fodder, fertilizers, and basic tools. These inputs will help boost productivity and food security for smallholder farmers and pastoralists affected by erratic rainfall and rising production costs. The project will also promote climate-smart agriculture and sustainable livestock practices to adapt to shifting environmental conditions.

To build economic resilience, the project includes business development support for rural entrepreneurs, especially women and youth, through training, mentorship, and market linkages. The establishment and strengthening of Village Savings and Loan Associations (VSLAs) will provide access to savings and micro-loans, enabling community members to invest in productive assets and diversify income sources.

Crucially, the project will strengthen local natural resource management structures, fostering collaboration among farmers, pastoralists, and local authorities. Community-based platforms will be supported to coordinate access to land, water, and grazing areas, thereby reducing the risk of conflict and ensuring more equitable, sustainable use of shared resources.

By combining support for livelihoods, financial inclusion, and governance of natural resources, the project will contribute to peaceful co-existence, improved food security, and long-term resilience for agro-pastoralist communities in White Nile.

### Objectives of the Midterm Assessment

The overall objective is to assess the relevance, effectiveness, efficiency, and emerging outcomes of the project to date, and to provide recommendations for improved implementation and impact.

#### Specific Objectives:

- Assess the relevance of the project design in addressing the current needs of agro-pastoralist communities, particularly in light of changing climatic and socio-economic conditions.

- Evaluate implementation progress against planned outputs and activities, including input distribution, training, VSLA formation, and business support.

- Measure the effectiveness of interventions in improving agricultural productivity, financial inclusion, income generation, and natural resource governance.

- Review the efficiency of resource utilization and coordination among implementing partners or stakeholders.

- Analyze gender and social inclusion, particularly women’s access to land, decision-making, and benefits from project activities.

- Examine the functionality and sustainability of natural resource management structures and their role in conflict prevention.

- Document lessons learned, challenges, and success stories that can inform adaptive management.

- Provide actionable recommendations for enhancing impact, scale, and sustainability in the remaining implementation phase.

### Key Evaluation Questions

- Relevance:

  - Are project interventions aligned with the needs and priorities of agro-pastoralist communities?

  - Is the project responsive to climate, economic, and conflict-related challenges in White Nile?

- Effectiveness:

  - What progress has been made toward achieving expected outputs and outcomes?

  - Have beneficiaries adopted improved practices in farming, grazing, or business management?

  - How effective are the VSLAs in improving financial resilience?

- Efficiency:

  - Are resources (inputs, staff, funding) being used effectively and timely?

  - Are there bottlenecks affecting delivery?

- Impact (Early Signs):

  - Are there observable changes in productivity, income, or conflict reduction?

  - How has participation in VSLAs and training influenced household resilience?

- Gender and Social Inclusion:

  - To what extent have women and marginalized groups been included in project activities?

  - Have there been improvements in women’s access to resources and decision-making?

- Sustainability:

  - Are community-based NRM structures active and effective?

  - What mechanisms are in place to ensure sustainability of inputs, VSLAs, and business services?

- Study Methodology

### The consultant will use a mixed-methods approach, combining quantitative and qualitative data collection. The methodology should include:

- Desk review of project documents (logframe, baseline data, progress reports, training materials)

- Key Informant Interviews (KIIs) with:

  - Project staff

  - Community leaders

  - Local authorities

  - NRM committee members

  - HHs Survey

- Focus Group Discussions (FGDs) with:

  - Agro-pastoralist beneficiaries (men and women)

  - VSLA members

  - Youth and women-led businesses

- Field visits to project sites to observe implementation and speak with participants

- Review of monitoring and performance data

All tools must be submitted to HAC office by the consultant, once the approval is out, the data collection will be carried out immediately by the service provider. All data will be collected using KOBO/ODK if possible.

Prior to field data collection, all the enumerators should be trained on the basics of data collection, including objectives of the study, structure of the questionnaires, sampling and how to collect data using tablets/ODK. A random sampling strategy will be employed to ensure representation across key demographic and geographic groups. Within each stratum, households/individuals will be randomly selected to minimize bias. This approach will enhance the reliability and generalizability of the findings while taking into consideration that the sampling will be done among each community, with the inclusion of all Kosti and Rabak targeted communities in the exercise.

Deliverables

| Deliverable | Description | Timeline |
| --- | --- | --- |
| Inception Report | Includes evaluation plan, tools, and methodology | Within 1 week of contract start |
| Field Data Collection | Conducted in selected locations | Weeks 2–3 |
| Draft Report | Preliminary findings and analysis | Week 4 |
| Validation Workshop | Present findings to stakeholders | Week 5 |
| Final Report | Final version incorporating feedback | Week 6 |

This study will consider:

- Ethical: The study will be guided by ethical considerations such as informed consent, safeguarding, sensitivity, openness, confidentiality and data protection, public access, broad participation, reliability and independence.

- Conflict sensitivity: the study will be guided by conflict sensitivity principles such as openness and transparency, considering the power relation and influencing forces operating in the targeted communities, inclusion, implementing multi-stockholders Multi-level meaningful consultation process

- Informed Consent and Voluntary Participation: Ensure that participation in the assessment is completely voluntary. Participants should be informed about the purpose of the assessment, what it involves, and their right to withdraw at any time without penalty. The data collectors should provide clear, understandable information about the assessment's objectives, risks, and benefits, allowing participants to make an informed decision to participate.

- Privacy and Confidentiality: The data collectors should gather data in a manner that ensures individual respondents cannot be identified, using coding systems where necessary. Strict measures for data storage and access to protect the confidentiality of the information collected will be also in place

- Child Safeguarding:  Ensure that all procedures are in the best interests of the child, considering their age, maturity, and psychosocial state. The data collectors should obtain consent from a parent or guardian for participants under the age of consent, unless doing so would compromise the child's safety. In such cases, established guidelines for ethical research involving at-risk children will be followed

- Do no Harm principle:  The exercise must include a risk assessment and take steps, if necessary, to mitigate identified risks. The risk assessment must look at negative consequences that may result from data collection.

- Cultural Sensitivity and Respect: This exercise will understand and respect the local culture, norms, and values and will engage with local communities and stakeholders in the planning and implementation phases to ensure cultural appropriateness and acceptance. The data collectors will use the local language or dialect for communication and materials.

- Gender Sensitivity: This exercise will recognize and address the different needs, experiences, and risks of men, women, boys, and girls in the assessment design and implementation. Particularly for any discussions around GBV safe Spaces for Disclosure should be provided, that is safe for participants to disclose sensitive information.

- People-centered and inclusive: The exercise should be guided by the interests and well-being of the population, which must participate and be included in all relevant phases; as well as being sensitive to age, gender, and other issues of diversity

Qualifications

- Bachelor’s degree in social sciences, social work, psychology or human services field required.

- 2+ years relevant experience in NGO, experience in livelihoods and food security.

- Excellent communication skills in English and Arabic, and presentation skills

- Excellent computer skills and other relevant electronics like use of projector, etc

Knowledge/Skills/Abilities

- Experience in data collection and analysis applying qualitative methods, ideally derived in a humanitarian context.

- Excellent process facilitation and interpersonal skills

- Very good time management skills

- Excellent analytical, interpersonal, communication and reporting skills.

Payment Schedule

The payment shall be 30% upon submission of the inception report and 70% upon submission of a satisfactory final report

All models, code, and documentation developed during this consultancy will become the property of NRC and will be made available to consortium partners. Selected components may be made available under appropriate open-source licenses as determined by the project leadership.

Application Deadline

Applications must be submitted to [ sd.procurement@nrc.no  ] by: 8th Sep 2025 @ 16:00 (GMT +2)

Interview dates:

Bids must include the following:

- The proposal includes outline of the evaluation framework and methods, including comments on the TOR, proposed time frame, and work plan (bids over 3 pages will be automatically excluded).

- Proposed evaluation budget

- CVs

Proposed Evaluation Criteria

- Technical Evaluation – 70 Points Total

| # | Criteria | Description | Score |
| --- | --- | --- | --- |
| 1 | Technical Expertise and Thematic Experience | Proven experience (with evidence) in leading monitoring, evaluation, and data collection exercises in humanitarian contexts (hunger, conflict, access, or displacement). Prior work with INGOs, UN agencies, or research institutions on similar evaluations. Demonstrated ability to analyse and synthesize findings into clear, actionable recommendations. | 35 |
| 2 | Understanding of Sudan and Conflict Settings | Strong understanding of Sudan’s humanitarian context, including livelihoods and food security challenges. Knowledge of displacement dynamics, local governance, and access constraints and demonstrated experience integrating gender and social inclusion in evaluation work. Preference will be given to consultants with Sudan-specific fieldwork or partnerships. | 25 |
| 3 | Proposed Methodology and Approach | Relevance and clarity of the proposed methodology, particularly in qualitative data collection (interviews, testimonies), integration of civilian voices, and working in insecure or remote settings. | 25 |
| 4 | Financial Offer (Cost-Effectiveness) | Realism and transparency of the financial offer, including justification for key cost lines (e.g. travel, co-researcher fees). Assessment will consider value for money, not just the lowest price. | 15 |
| TOTAL |  |  | 100 |

To: Norwegian Refugee Council

Sir / Madam, We offer to deliver the service in accordance with all requirements of the current Request for Proposal, Conditions of Contract and any other Binding requirements accompanying this Bid. We, the undersigned, verify that we are in compliance with all applicable laws and regulations, and meet the ethical standards as listed above or positively agree to these ethical standards and are willing to implement necessary changes in the organization.

This Bid signed by our authentic representative and your written award of it shall constitute the formation of a binding contract between us.

| Registered company name: |  |
| --- | --- |
| Any other trading names: |  |
| Any associated companies (cross holding/ joint ownership/ shareholding/ etc.) |  |
| Name of Signatory: | Date of Signing: |
| Title of Signatory: | Name of Bidder: |
| Signature & stamp: | Tel N°: |
|  | Email: |
|  | Address: |

| Bank name (to be used for this contract) |  |
| --- | --- |
| Account number |  |

| Questions | Answers |
| --- | --- |
| What is the currency of the offer? (SDG, USD, EUR , other…) Note that NRC will favour quotes in SDG. Please read below regarding USD payments. DO NOT PROVIDE QUOTES IN BOTH SDG AND USD CURRENCIES. |  |
| Please confirm your offer inclusive Net price after the deduction of discounts |  |
| Please confirm your prices include all taxes and fees (net prices): (If not, please explain and detail the taxes & fees) |  |
| If your offer is in USD => payment will be made by bank transfer. - Do you have a EUR account in Sudan? if YES, then in which bank. - Do you have a EUR account abroad? if YES, then in which bank. (Please provide bank details for each account with Company name) |  |
| Do you accept payment after completion of Service? BY Instalment within 30 days of receipt of the invoice |  |
| What is the validity period of your offer? (In calendar days) (Preferable 90 days) |  |

4 - Accepted methods for submission of quotation/offer:

We recommend you fill up this Request for Quotation directly on your computer.

You can also print it and fill it up by hand if you have not access to a computer.

You can submit the price offer by using the table on page 2, or by using your own proforma document.

Your quotation / offer must be signed and stamped on all pages (including the present Request for Quotation).

4 - Your Company details:

- General information

| Name of the company |  |  |
| --- | --- | --- |
| Name of the owner(s) Date of birth of the owner(s) (Mandatory for screening) |  |  |
| Address of the company |  |  |
| Name of contact person |  |  |
| Position |  |  |
| Email |  |  |
| Phone |  |  |

- Company bank account details:

| Beneficiary name: |  |  |
| --- | --- | --- |
| Beneficiary account no.: |  |  |
| Beneficiary Bank: |  |  |
| Bank branch: |  |  |
| SWIFT: |  |  |
| IBAN: |  |  |
| Bank address: |  |  |

- References

Please provide details of at least 5 client references whom NRC may contact, preferably from INGOs and UN agencies, for similar service:

| Client/company name | Contact person | Phone | Email | Contract details (works, location, size, value, etc) |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| … |  |  |  |  |

5 - Mandatory documents to attached to your quotation / offer:

| Mandatory documents | Checked (Y/N) / Open Ended Question |
| --- | --- |
| Certified copy of accreditation – Compulsory |  |
| NRC Request for Quotation (filled up, signed and stamped) - You can use the RFP table above - Or any other format of your choice but specifying all items in the RFP list. You must Sign and Stamp each page. |  |
| Technical Expertise & Thematic Experience - What experience do you/your organization have in leading monitoring, evaluation, and data collection exercises in humanitarian contexts (e.g., hunger, conflict, displacement, or access-restricted areas)? - Can you provide examples of past work with INGOs, UN agencies, or research institutions on similar evaluations? - How do you ensure that findings are analyzed, synthesized, and translated into clear, actionable recommendations? |  |
| CV/resume highlighting relevant experience |  |
| Understanding of Sudan & Conflict Settings - What is your understanding of Sudan’s humanitarian context, particularly in livelihoods, food security, and displacement dynamics? - How have you previously worked in fragile or conflict-affected environments (e.g., Sudan, South Sudan, Yemen, Syria)? - How do you integrate gender and social inclusion into your evaluation work, particularly around women’s access to resources and decision-making? - Do you have fieldwork experience or partnerships in Sudan that strengthen your contextual knowledge? |  |
| Proposed Methodology & Approach - What methodology will you use for this midterm assessment (covering inception, data collection, analysis, reporting)? - How will you integrate qualitative data collection methods (e.g., KIIs, FGDs, testimonies) alongside quantitative surveys? - How will you ensure that the voices of affected communities are included and represented? - What measures will you use to ensure data collection in insecure, fragile, or remote settings? |  |
| Financial Offer – Cost Effectiveness - Please provide a detailed financial proposal, including justification for key cost lines (e.g., travel, enumerator fees, translation, training, report writing). - How does your financial offer ensure value for money while maintaining quality? |  |

Please check that you are providing all of the below mentioned document

You can also attach additional documents such as photos, company profile, certifications…

6 - Other information:

Payment will be made by bank transfer.

All suppliers doing business with NRC should maintain high standards on ethical issues, respect and apply basic human and social rights, ensure non-exploitation of child labour, and give fair working conditions to their staff. NRC reserves the right to reject quotations provided by suppliers not meeting these standards.

Vendors doing business with NRC will be screened on anti-corruption due diligence before NRC confirms an order or contract.

NRC aims to purchase products and services that the minimum environmental impact. Environmental considerations form part of the NRC selection criteria, and NRC reserves the right to reject quotations provided by suppliers not meeting these standards.

NRC is obliged to ensure that its procurement decisions are clearly justified and documented and keeping within the Donors mandatory principles. In that regard, full and on-the-spot access must be granted to representatives of NRC, the Donor or any organisation or person mandated by it, to premises belonging to NRC or its contractors. The right to access shall include all documents and information necessary to assess, or audit the implementation of the contract

NRC reserves the right to accept or reject the whole or part of your quotation based on the information provided. Incomplete quotations which do not comply with our conditions will not be considered.

Shortlisted suppliers may be required to submit samples of each item. Please be sure to have all samples available at short notice, and wait for a response from NRC if you have been shortlisted.

Ethical Standards Declaration for all Supply, Service and Works Contractors

We, the undersigned, (‘we’, ‘our’ or ‘us’) CONSIDERING THAT:

FIRST, we are bidding for, or entering into, a contract with the Norwegian Refugee Council (NRC) to supply goods, services or works to NRC (‘the Contract’).

SECOND, we understand that as a humanitarian organisation, NRC expects its suppliers and contractors to have high ethical standards.

THIRD, we understand that NRC therefore needs us to confirm that we adhere to the required ethical standards (‘the ethical standards’) by signing this declaration (‘the Declaration’).

THEREFORE, we DO HEREBY DECLARE as follows:

- Declaration concerning compliance with applicable laws and these ethical standards

We declare that we shall:

- Meet the ethical standards in this declaration (‘ethical standards’)

- Ensure that any party representing us, including but not limited to:

•	board members

•	directors

•	employees

•	contractors or sub-contractors, and their employees

•	consultants and sub-consultants, and their employees;

•	other legal representatives

(‘our Representatives’) are aware of and comply with these ethical standards.

In the event that we, or our Representatives, do not meet the ethical standards at present, we shall:

- Explain to NRC in what way we do not currently meet the ethical standards

- Agree a plan and timeline with NRC to implement changes that allow us to meet the ethical standards

- Provide regular updates to NRC on the implementation plan.

- Declaration concerning status

We hereby declare that neither we, nor to the best if our knowledge our Representatives, are in any of the following situations:

  - Have made an offer, payment, consideration or benefit of any kind, which constitutes illegal or corrupt practice, directly or indirectly, as an inducement or reward in relation to the tendering, awarding or execution of the Contract.

  - Are involved in any form of fraud, corruption, collusion, coercive practice, bribery, involvement in a criminal organisation or other illegal activity

  - Are insolvent, in receivership, bankrupt, or being wound up

  - Have suspended activities

  - Are subject to legal proceedings related to 2.1

  - Have at any time been found guilty and sentenced by a court, whether in the country of employment or abroad, for a criminal offence in respect of children or vulnerable adults

  - Are engaged in:

•	terrorism or the material support of terrorism

•	the sale or manufacture, either directly or indirectly, of anti-personnel mines or any components produced primarily for the operation thereof

•	the sale or manufacture, either directly or indirectly, of weapons

•	the production of alcohol, tobacco, or pornography.

- Declaration concerning Conflicts of Interest

We declare that neither we nor, to the best of our knowledge, our Representatives have an undisclosed conflict of interest with NRC, in accordance with NRC’s Conflict of Interest Policy (the Policy).

Where any potential conflict of interest exists between our Representatives and NRC or any NRC staff member, we shall notify NRC in writing of the potential conflict using Form F in the Policy. We understand that the Policy and the Form is available on NRC’s website or that we can contact the NRC Procurement focal point, as mentioned in the tender documentation. NRC shall then determine whether action is required.

A conflict of interest can be due to a relationship with an NRC staff member such as family or friends.

We understand that if we fail to report a potential conflict of interest and are later found to have a conflict of interest, we may be removed from the NRC vendor database.

- Declaration concerning compliance with national law

We declare that we and, to the best of our knowledge, our Representatives:

  - comply with all applicable laws and regulations in effect in the country or countries where the Contract will be carried out.

  - comply with all applicable export laws concerning the country or countries where the Contract will be carried out.

  - are registered with the relevant government authority with regard to taxation for the duration of the Contract.

  - pay taxes according to all applicable national laws and regulations for the duration of the Contract.

- Declaration concerning compliance with labour standards

We declare that we and, to the best of our knowledge, our Representatives:

We declare that we and, to the best of our knowledge, our Representatives comply with applicable national labour law standards and the International Labour Organisation Declaration on Fundamental Principles and Rights at Work.

Specifically, we declare that we and, to the best of our knowledge, our Representatives comply with the following minimum labour standards:

  - Working Conditions

- All workers receive a contract of employment that is written in a language they understand.

- All workers are free to leave after giving reasonable notice.

- All workers have the right to join or form trade unions of their own choosing and to bargain collectively.

- No worker is required to lodge ‘deposits’ or identity papers or immigration documents in order to obtain employment.

  - Wages and benefits

  - Wages and benefits paid for a standard working week meet, at a minimum, national legal standards or industry benchmark standards, whichever is higher. Wages are always sufficient to meet basic needs.

  - No deductions from wages are made as a disciplinary measure.

  - Working time

  - Working hours comply with national laws and benchmark industry standards, whichever affords greater protection. Whenever possible working hours do not exceed 48 hours per week (8 hours per day).

  - Workers are provided with at least one day off for every 7-day period.

  - Health and safety

  - Steps are taken to prevent accidents and injury to health arising out of, associated with, or occurring in, the course of work, by minimizing, so far as is reasonably practicable, the causes of hazards inherent in the working environment.

  - Workers receive regular and documented health and safety training, and such training is repeated for new workers.

  - Workers have access to clean toilet facilities and to potable water, and, if appropriate, sanitary facilities for food storage is provided.

  - Accommodation, where provided, is clean, safe and adequately ventilated.

  - Discrimination and abuse

  - No worker is forced, bonded or an involuntary prison worker.

  - There is no discrimination at the workplace based on ethnic background, religion, age, disability, gender, marital status, sexual orientation, union membership or political affiliation.

  - Measures are in place to protect workers from sexually intrusive, threatening, insulting or exploitative behaviour, and from discrimination or termination of employment on unjustifiable grounds, e.g. marriage, pregnancy, parenthood or HIV status.

  - Physical abuse or punishment, or threats of physical abuse, sexual or other harassment and verbal abuse, as well as other forms of intimidation, are prohibited.

  - Persons under 18

- No persons under the age of 18 shall be engaged in work which is hazardous to their health or safety, including night work.

- The working hours and nature of work of any worker who is under the age of 18 shall not interfere with their opportunity to complete his or her education.

- Declaration concerning the environmental standards

We declare that we and, to the best of our knowledge, our Representatives comply with applicable national environmental law standards and with international environmental standards, to the greatest extent possible.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We respect national and international environmental legislation and regulation.

  - We ensure that production and extraction of raw materials for production does not contribute to the destruction of the resources and income base for marginalised populations, such as in claiming large land areas or other natural resources on which these populations are dependent.

  - We take environmental measures into consideration throughout the production and distribution chain ranging from the production of raw material to the consumer sale. This includes reasonable steps to minimise negative environmental impacts (e.g. emissions, water usage, waste) and to use - where possible - sustainable resources. Local, regional and global environmental aspects shall be considered. The local environment at the production site will not be exploited or degraded by pollution and waste.

  - We carefully manage hazardous chemicals and other substances in accordance with documented safety procedures.

- Declaration concerning protection from sexual exploitation and abuse

We and, to the best of our knowledge, our Representatives comply with international standards related to protection from sexual exploitation and abuse (PSEA) and sexual harassment.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We take sexual misconduct seriously and ensure that any employee found to have carried out sexual misconduct will be subject to disciplinary action.

  - We will ensure, that none of our employees engage in any sexual activity with persons (adult or child) in relation with this contract regardless of the age of majority or consent locally.

  - We will ensure that none of our employees produce, procure, distribute or use sexually explicit material in any activities under the Contract or on any sites used under the Contract.

  - We will ensure that none of our employees will exchange money, employment, goods or services for sex, including sexual favours or other forms of humiliating, degrading, or exploitative behaviour.  This prohibition extends to any use of sex trade workers.  If  any sexual misconduct is found to have taken place, such employees face disciplinary action.

  - We shall report any incident or complaint of sexual misconduct or child abuse related to the activities carried out under the Contract through NRC’s PSEA and Safeguarding Unit at psea@nrc.no.

  - We shall report any known or reported sexual relationship between our employees and NRC staff to NRC.

- Declaration concerning protection of children

We declare that neither we nor, to the best of our knowledge, our Representatives are engaged in any practice inconsistent with the rights set forth in the Convention on the Rights of the Child.  We commit to upholding international and national laws and policies regarding child safeguarding.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We support and protect the complainant, survivors and witnesses of any raised incidents or complaints of sexual misconduct or child abuse.

  - We will ensure, that our employees will not abuse or exploit children or act in a manner that may place a child at risk of harm.

  - We will ensure that our employees are not left alone with children.

  - We will ensure our employees will not ask children for personal contact details without a valid reason to do so.

  - We listen, to the best of our ability, to children’s views and opinions and treat boys and girls in a manner that is respectful of their rights and dignity during the performance of the Contract.

  - We shall report any suspicion of child safeguarding concerns through the Complaints and Feedback Mechanism, provided by the NRC contract focal point and at psea@nrc.no.

- Declaration concerning anti-human trafficking

We declare that neither we nor, to the best of our knowledge, our Representatives are engaged in trafficking in persons as defined in the protocol to Prevent, Suppress and Punish Trafficking in Persons or the UN Convention against Transnational Organized Crime.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We do not solicit persons for the purpose of employment, or offer employment by means of materially false or fraudulent pretences, representations, or promises.

  - We do not charge employees recruitment fees.

  - We do not provide or arrange housing for employees that does not meet host country housing and safety standards.

  - We commit to report any suspected violations of this clause to NRC immediately.

  - We commit to make our Representatives aware of the trafficking related prohibitions outlined above and share the Global Human Trafficking Hotline Information with them (1-844-888-FREE, help@befree.org).

- General

We understand that:

  - The Declaration will be kept on file for a period of 10 years.

  - The Declaration will be updated every year or more often as appropriate.

  - We must inform NRC immediately in the event that there is a change to the Declaration.

  - NRC may perform checks to verify that the ethical standards are adhered to and shall be granted reasonable access to our premises and to our documentation, computer systems etc, in order to be allowed to do so.

  - In the event that NRC deem that we fail to meet or are not taking appropriate steps to meet, the ethical standards, NRC may immediately terminate any and all contracts and agreements we have with them and at no cost to NRC.

- Requirement to notify NRC

We shall immediately notify NRC through the Complaints and Feedback Mechanism, provided by the NRC contract focal point if:

  - Any allegations of alleged corruption, sexual exploitation or abuse, or child abuse are made against us or, to the best our knowledge, our Representatives, during the Contract, whether relating to the Contract or not.

  - Any allegations are made, or any changes occur, in relation to any of the declarations made herein

Signed on our behalf as follows:

| Signature |  |
| --- | --- |
| Name |  |
| Position |  |
| Date |  |
| Place |  |