Terms of Reference (ToR)

Research on Promoting a Diverse Range of Locally Adapted Seed Varieties and Animal Breeds in Gedarif State

| Activity | Research on Promoting a Diverse Range of Locally Adapted Seed Varieties and Animal Breeds in Gedarif State |
| --- | --- |
| Project | Enhancing Food Security and Resilience of Rural Communities in Sudan (EFSR Project) |
| Location | Kassala & Gedarif States, Sudan |
| Duration | 24 Months |
| Implementing Partner | Practical Action Sudan |
| Supporting Agency | UNPOS, European Union |

1. Background

The Enhancing Food Security and Resilience (EFSR) project aims to strengthen the livelihoods and adaptive capacity of smallholder farmers and pastoralists in Gedarif State. Gedarif is characterized by diverse agro-ecological zones, where smallholder farmers and pastoral communities rely heavily on locally adapted crops and livestock for food security, income, and resilience against climate change.

The sustainability of local agricultural systems depends on the availability and use of locally adapted seed varieties and resilient animal breeds. Currently, there is limited documentation and understanding of the diversity, adaptation, and utilization of these resources in key villages within Gedarif State. This research seeks to fill this gap and provide actionable recommendations for promoting local agrobiodiversity.

Target Locations: Aldaroat, Jemaza, Halat Khater, Salmeen Shariq, Umsagata, Ban villages as well as Tadamun area.

2. Objective of the Research

The main objective of the research is to identify, document, and promote the use of locally adapted seed varieties and animal breeds to enhance food security, resilience, and sustainable livelihoods in Gedarif State.

Specific Objectives:

- Identify and document locally adapted crop varieties and livestock breeds in the target villages.

- Assess the current use, availability, and constraints of these local varieties and breeds.

- Evaluate farmers’ and pastoralists’ knowledge, preferences, and perceptions regarding local biodiversity.

- Recommend strategies for promoting diverse, locally adapted seeds and animal breeds to strengthen resilience and food security.

3. Scope of Work

The research will cover:

- Field surveys and interviews with farmers, pastoralists, community leaders, and local authorities.

- Collection of information on crop and livestock varieties, including morphological, agronomic, and socio-economic characteristics.

- Mapping the availability and distribution of locally adapted seeds and animal breeds.

- Identification of barriers and opportunities for promoting local varieties and breeds.

- Development of recommendations and strategies for scaling up the use of local agrobiodiversity in the target areas.

4. Methodology

The research should adopt a participatory and mixed-methods approach:

- Desk Review: Review existing literature, reports, and government records on local crop varieties and livestock breeds.

- Field Surveys: Conduct structured questionnaires, focus group discussions, and key informant interviews in the target villages.

- Participatory Rural Appraisal (PRA): Engage farmers and pastoralists in ranking, mapping, and describing local varieties and breeds.

- Data Analysis: Use qualitative and quantitative methods to analyze the collected information and identify patterns, gaps, and recommendations.

5. Deliverables

- Inception Report including methodology, work plan, and tools for data collection.

- Draft Research Report summarizing findings from all target villages.

- Final Research Report with:

  - Comprehensive documentation of local seed varieties and animal breeds.

  - Analysis of availability, utilization, and constraints.

  - Recommendations for promoting local agrobiodiversity.

- Presentation of Findings to project stakeholders, including local communities, government agencies, and partners.

6. Timeline

The research is expected to be completed within 4 weeks from the start date. A proposed timeline:

| Activity | Duration | Timeline |
| --- | --- | --- |
| Desk review & preparation | 5 days | Week 1 (Days 1–5) |
| Field data collection | 10 days | Week 2–3 (Days 6–15) |
| Data analysis | 5 days | Week 3–4 (Days 16–20) |
| Draft report preparation | 4 days | Week 4 (Days 21–24) |
| Validation & stakeholder feedback | 3 days | Week 4 (Days 25–27) |
| Final report submission | 2 days | Week 4 (Days 28–29) |

7. Qualifications of the Researcher/Team

- Advanced degree in Agronomy, Animal Science, Agricultural Economics, or related fields.

- Proven experience in agricultural research, particularly in crop and livestock diversity.

- Experience in participatory research methods and working with smallholder farmers and pastoralists.

- Strong report-writing and communication skills in English and Arabic (local language proficiency is an advantage).

8. Reporting and Supervision

- The research team will report to the EFSR Project Manager.

- Regular updates should be provided weekly, with review and feedback sessions scheduled after each major milestone (inception report, draft report).

9. Budget

The budget will cover:

- Fieldwork costs (transportation, accommodation, and per diem)

- Data collection materials and equipment

- Analysis and report production

- Note: Practical Action will cover costs related to workshops or validation meetings with stakeholders. These expenses are not included in this budget.

10. Expected Impact

- Strengthened knowledge and awareness of locally adapted seeds and animal breeds.

- Enhanced capacity of smallholder farmers and pastoralists to use diverse, resilient resources.

- Improved strategies for sustainable agricultural development and food security in Gedarif State.

Top of Form

Bottom of Form