Term of reference

Primary Health Care provision for vulnerable populations affected by food insecurity and malnutrition in Sudan

Midterm Evaluation Study

| PROJECT SUMMARY |  |
| --- | --- |
| Type of evaluation | Midterm Evaluation Study |
| Name of the project | Integrated Health, Nutrition, PSS and WASH Support for Vulnerable Populations in Red Sea, Blue Nile and Central Darfur |
| Project Start and End dates | 01 November 2024 |
| Project duration | 31 October 2027 |
| Project locations | Sudan: Red Sea State (Haya and Sawakin localities), Blue Nile State (Bau and Geissan localities), and Central Darfur State (Central Jebel Marra locality) |
| Thematic areas | Primary Health Care (PHC), Nutrition, Psycho-Social Support (PSS), Water, Sanitation and Hygiene (WASH), Health Systems Strengthening, Community Engagement |
| Donor | [Insert donor name] EU |
| Key stakeholders | State Ministry of Health; Local Health Teams; health and nutrition facility staff; community health and nutrition committees; community health workers and volunteers; local authorities; implementing partners; IDPs, refugees and host communities |
| Estimated beneficiaries | Direct target group: 176 primary health care staff and 64 nutrition service providers. Final beneficiaries: 215,401 people, including 56,010 women, 54,363 men, 54,105 girls, and 50,923 boys |
| Overall objective of the project | To contribute to improved health conditions of vulnerable populations affected by extreme poverty, food insecurity and malnutrition in Sudan, including IDPs, refugees and host communities |
| Specific objective of the project | To increase sustainable access to and demand for quality Primary Health Care (PHC), Nutrition, Psycho-Social Support (PSS) and Water, Sanitation and Hygiene (WASH) services in targeted states, including for host communities, internally displaced persons (IDPs) and refugees |

- Background

Sudan continues to face a severe humanitarian crisis driven by protracted conflict, displacement, poverty, food insecurity, malnutrition, and weak access to essential services. Within this context, the Action aims to improve the health conditions of vulnerable populations affected by extreme poverty, food insecurity, and malnutrition, including internally displaced persons (IDPs), refugees, and host communities. The specific objective of the Action is to increase sustainable access to and demand for quality Primary Health Care (PHC), Nutrition, Psycho-Social Support (PSS), and Water, Sanitation and Hygiene (WASH) services in targeted states.

The Action targets health and nutrition systems as well as vulnerable communities. Direct target groups include 176 primary health care staff and 64 nutrition service providers working in health and nutrition facilities, who will benefit from capacity building, mentoring, and incentive packages to support staff retention. Indirectly, the Action is expected to benefit 215,401 people in the catchment areas of 16 health and nutrition facilities located in Red Sea State (7 facilities in Haya and Sawakin localities), Blue Nile State (7 facilities in Bau and Geissan localities), and Central Darfur State (2 facilities in Central Jebel Marra locality). Final beneficiaries include 56,010 women, 54,363 men, 54,105 girls, and 50,923 boys.

The Action is structured around three outputs:

- Improving PHC, Nutrition, and WASH services at facility and community level, including for IDPs, refugees, host communities, women, girls, and persons living with disabilities.

- Strengthening the management capacity and accountability of local health systems.

- Reducing socio-cultural, behavioural, and gender-related barriers to health and nutrition.

To achieve these outputs, the Action includes rehabilitation and construction of health and nutrition facilities, provision of medicines, equipment, therapeutic and supplementary feeding products, incentives for health and nutrition staff, solarization, referral support, training for local health teams, supportive supervision, HMIS strengthening, establishment or reactivation of community health and nutrition committees, support to community health workers and volunteers, barrier analysis, community sensitization, outreach services, and child-led health and nutrition initiatives.

The midterm evaluation is intended to assess progress made toward the project objectives, review the continued relevance of the Action, and generate evidence on implementation performance, emerging results, challenges, and areas requiring adjustment during the remaining project period.

| Area | Description |
| --- | --- |
| Output 1.1 | Improvement of PHC, Nutrition, and WASH services at PHC centres and community level, including for IDPs, refugees, host communities, women, girls, and persons living with disability. |
| Output 1.2 | Strengthening the management capacity and accountability of local health systems. |
| Output 1.3 | Reduction of socio-cultural, behavioural, and gender barriers to health and nutrition. |
| Cross-cutting assessment focus | The evaluation should also examine how effectively the activities under each output have been implemented and whether they are contributing to the project’s specific objective. |

- Purpose of Midterm Study

The purpose of the midterm evaluation is to assess the continued relevance, implementation progress, and emerging results of the Action in relation to its stated objective, outputs, and activities. The study will provide an evidence-based review of how effectively the project is progressing in improving access to and demand for quality PHC, Nutrition, PSS, and WASH services in the targeted states.

Specifically, the midterm evaluation will:

- assess the relevance of the intervention in the current humanitarian and service delivery context;

- review progress toward the Action’s outputs and intended outcome;

- examine the extent to which planned activities have been implemented across the three target states;

- assess the quality, reach, and early effectiveness of project interventions at facility, community, and system levels;

- identify strengths, implementation challenges, and operational bottlenecks;

- assess whether the Action is adequately addressing the needs of IDPs, refugees, host communities, women, girls, and persons living with disabilities;

- provide practical recommendations to improve implementation, quality, accountability, and results during the remaining project period;

- contribute to learning and accountability for Save the Children, partners, donors, government counterparts, and targeted communities.

This midterm evaluation will serve as an important learning and decision-making point, helping to strengthen implementation and improve results during the remainder of the Action period.

III. Study Methodology

### 3.1 Study Design

The midterm evaluation will apply a mixed-methods design, combining quantitative and qualitative approaches to generate a comprehensive understanding of project performance, relevance, and emerging results. The methodology will include both primary and secondary data sources and will assess progress across the three target states: Red Sea, Blue Nile, and Central Darfur.

The study will be implemented in a multi-stage process:

### Stage 1: Methodological and Scoping Workshop

The first stage will involve a methodological workshop to guide the overall study approach and ensure shared understanding among key stakeholders. This workshop will be conducted with project partners, with particular participation from the State Ministry of Health (SMoH) and other relevant stakeholders.

During this workshop, the consultant will present the proposed:

- methodological approach;

- study design;

- data collection methods and tools;

- sample size;

- sampling techniques; and

- overall implementation approach.

The purpose of the workshop will be to review, discuss, and validate the proposed methodology before the start of field activities, and to ensure that the study approach is contextually appropriate, methodologically sound, and aligned with stakeholder expectations.

### Stage 2: Desk Review and Secondary Data Analysis

The second stage will involve a review of available project documents and secondary data to understand project design, progress, context, and information gaps. This may include:

- project proposal and logframe;

- baseline and monitoring data;

- routine project reports;

- HMIS and LMIS records where available;

- training and supervision records;

- barrier analysis reports;

- project output tracking data; and

- other relevant assessments and contextual documents.

The findings from the desk review will inform the refinement of the evaluation questions, tools, and sampling approach.

### Stage 3: Primary Data Collection

The third stage will involve field-based primary data collection using a combination of:

- household or beneficiary surveys, where applicable;

- focus group discussions (FGDs);

- key informant interviews (KIIs);

- facility observation checklists; and

- interviews with health facility staff, local health teams, community health workers and volunteers, and community representatives.

All tools will be developed in English and Arabic, and data collection will be conducted using a standardized methodology to ensure quality and consistency.

### 3.2 Data Sources and Data Collection Methods / Tools

#### Primary Data Sources

Primary data may be collected from:

- beneficiaries in the catchment areas of targeted health and nutrition facilities;

- health facility staff and nutrition service providers;

- local health teams;

- community health and nutrition committees;

- community health workers and volunteers;

- mothers’ groups and other community structures;

- local authorities and State Ministry of Health representatives; and

- implementing partners and relevant humanitarian actors.

#### Secondary Data Sources

Secondary data may include:

- project proposal and logical framework;

- baseline or earlier assessments, if available;

- routine monitoring data;

- HMIS and LMIS data;

- supportive supervision reports;

- training records;

- supply and referral records;

- barrier analysis reports;

- donor and internal progress reports; and

- relevant government or humanitarian sector reports.

#### Data Collection Tools

Data collection tools may include:

- structured questionnaires;

- FGD guides;

- KII guides;

- health facility observation checklists; and

- document review matrix.

All primary data should facilitate disaggregation by sex, age, location, and, where feasible, displacement status and disability.

### 3.3 Sampling

The midterm evaluation should adopt a sampling approach that is representative of the project target population and sufficiently robust to assess progress across the key participant categories and targeted states.

A stratified sampling approach is recommended, with stratification by:

- state: Red Sea, Blue Nile, Central Darfur;

- locality and/or facility catchment area; and

- participant category, as relevant.

The sampling should ensure proportional representation across the 16 targeted health and nutrition facilities:

- 7 facilities in Red Sea,

- 7 facilities in Blue Nile, and

- 2 facilities in Central Darfur.

The final sampling methodology and sample size should be clearly proposed and justified during the inception phase and presented in the methodological workshop for validation, taking into account:

- the project’s target groups and final beneficiaries;

- geographic spread and access constraints;

- the need for credible, practical, and analytically useful findings; and

- the balance between quantitative breadth and qualitative depth.

### 3.4 Data Collection

All required approvals should be secured from the relevant authorities before fieldwork begins. Data collection will preferably be conducted using KOBO/ODK or another suitable digital platform where feasible.

A trained and gender-balanced data collection team should be used. Quality assurance measures should include:

- tool piloting and revision;

- enumerator training;

- close field supervision;

- daily review of submitted forms;

- checks for consistency, completeness, and accuracy;

- timely correction of errors and clarification of unclear responses.

Enumerators and field teams should be trained in:

- the objectives of the study;

- use of tools and devices;

- sampling procedures;

- ethical data collection;

- safeguarding and referral considerations, especially when engaging children or vulnerable groups.

### 3.5 Data Analysis and Reporting

Save the Children will lead and/or oversee the analysis process. A clear data analysis plan should be developed to ensure systematic triangulation of findings from multiple data sources.

#### Quantitative Data

Quantitative data collected through KOBO or similar systems will be cleaned, exported, and analysed using Excel and/or other suitable software. Analysis should include:

- descriptive statistics;

- comparisons across states and participant groups where relevant;

- presentation of findings in tables, charts, and graphs.

#### Qualitative Data

Qualitative data from interviews, FGDs, observations, and document review will be synthesised thematically and triangulated with quantitative findings to provide explanatory depth and contextual understanding.

The final analysis should assess:

- progress against outputs and intended outcome;

- implementation quality and coverage;

- emerging results and operational constraints;

- cross-state similarities and differences;

- implications for the remainder of the Action.

A draft report will be shared internally for feedback, followed by a final report.

### 3.6 Ethical Procedures

All data collection must adhere to ethical research standards and Save the Children procedures. This includes:

- informed consent from all participants;

- confidentiality and data protection;

- safeguarding and protection from harm;

- sensitivity when collecting information from vulnerable groups;

- appropriate referral pathways if protection concerns arise.

The study should also ensure:

- inclusion of women, men, girls, boys, persons with disabilities, IDPs, refugees, and host communities where relevant;

- child-sensitive and conflict-sensitive data collection approaches;

- translation of tools into Arabic;

- training for enumerators on ethical and sensitive data collection.

- Expected Deliverables

The study deliverables and indicative timeline are outlined below, adjusted for a study start in May 2026.

| Deliverable | Timeline |
| --- | --- |
| Kick-off of the Midterm Evaluation and planning | Week 1 (1–7 May 2026) |
| Methodological Workshop | Week 1 (1–7 May 2026) |
| Development, review and finalization of data collection tools | Week 1 (1–7 May 2026) |
| Approvals from relevant authorities | Week 1–2 (1–14 May 2026) |
| Training and piloting | Week 2 (8–14 May 2026) |
| Data collection | Week 3–4 (15–28 May 2026) |
| Data cleaning and analysis | Week 5 (29 May–4 June 2026) |
| Draft Midterm Evaluation Report | Week 5 (29 May–4 June 2026) |
| Debriefing Session on Preliminary Findings | Week 5 (29 May–4 June 2026) |
| Final Midterm Evaluation Report | By 7 June 2026 |
| Dissemination Workshop for Sharing the Final Report with Partners | After submission of the final report / by 7 June 2026 |