# Request for Bid

| Tender Name: Repair and Rehabilitation of 2 Hand Pumps and 1 Water Yard in Alrahad village of Gedaref State |  | Tender No: SD-MC-518785-CW-RFQ |
| --- | --- | --- |
| Location: (Gedaref, Sudan) | Correspondence Language(s): English |  |
| Brief Summary Description of Project: Mercy Corps is interested in receiving a detailed bid from the Contractors for the rehabilitation of 2 community Hand Pumps and 1 Water Yard ( Alshamam, Makankana-H/Ps) Wad Abakar-W/Y) in Al Rahad Locality |  |  |

| Request for Bid Available from: June 13th, 2026 | Request for Bid to be send through: SD-TENDERS@MERCYCORPS.ORG |
| --- | --- |
| Deadline for Offer Submission: June 21st, 2026 | Submit Offers to: - SD-TENDERS@MERCYCORPS.ORG |

Mercy Corps reserves the right to accept or reject any late offers

| Questions and Answers (Q&A) |  |
| --- | --- |
| If any, Submit Questions in writing to: sd-tenders@mercycorps.org Copy: jwandera@mercycorps.org |  |
| Last Day for Questions: | Questions will be answered by: James Wandera |
| Questions will be answered through: sd-tenders@mercycorps.org |  |

| Q&A Session N/A |  |
| --- | --- |
| Date / Time: (Day / month in letter / year; Time) | Location: |
| Point of Contact: |  |

| Documentation Checklist |  |
| --- | --- |
| These documents are contained within this RFB: | - Request for Bid - General Conditions for Tender - Criteria and Submittals - Price Offer Sheet - Supplier Information Form - Modern Slavery Questionnaire - Scope of Work/Technical Specifications/BOQ - Sample Contract |

# General Conditions for Tender

Mercy Corps invites offers for the goods, services and/or works described and summarized in these documents, and in accordance with procedures, conditions and contract terms presented herein. Mercy Corps reserves the right to vary the quantity of work/materials specified in the RFB without any changes in unit price or other terms and conditions and to accept or reject any, all, or part of submitted offers.

2.1	Mercy Corps’ Anti-Bribery and Anti-Corruption Statement

Mercy Corps strictly prohibits:

- Any form of bribe or kickback in relation to its activities

This prohibition includes any request from any Mercy Corps employee, consultant or agent for anything of value from any company or individual in exchange for the employee, consultant or agents taking or not taking any action related to the award of a contract or the contract once awarded.  It also applies to any offer from any company or individual to provide anything of value to any Mercy Corps employee, consultant or agent in exchange for that person taking or not taking any action related to the award of the contract or the contract.

- Conflicts of interests in the awarding or management of contracts

If a company is owned by, whether directly or indirectly, in whole or in part, any Mercy Corps employee or any person who is related to a Mercy Corps employee, the company must ensure that it and the employee disclose the relationship as part of or prior to submitting the offer.

- The sharing or obtaining of confidential information

Mercy Corps prohibits its employees from sharing, and any bidders from obtaining, confidential information related to this solicitation, including information regarding Mercy Corps’ price estimates, competing bidders or competing offers, etc.  Any information provided to one bidder must be provided to all other bidders.

- Collusion between/among bidders

Mercy Corps requires fair and open competition for this solicitation.  No two (or more) companies submitting bids can be owned or controlled by the same individual(s). Companies submitting offers cannot share prices or other offer information or take any other action intended to pre-determine which company will win the solicitation and what price will be paid.

- Any form of exploitation, abuse, human trafficking or internal sexual misconduct

Mercy Corps requires its partners to adhere to its Safeguarding policies including the its policies on Child Safeguarding, Prevention of Sexual Exploitation and Abuse of Beneficiaries and Community Members, Anti-Trafficking and Sexual Misconduct (available at https://www.mercycorps.org/who-we-are/ethics-policies). Companies will be expected to ensure that they have the capacity to abide by these policies, that their employees and subcontractors understand these policies, and that they communicate to its employees and subcontractors the duty to report any violation or suspected violation. Mercy Corps will not engage with a company that is found to be in violation of these policies.

Violations of these prohibitions, along with all evidence of such violations, should be reported to:

http://mercycorps.org/integrityhotline

Mercy Corps will investigate allegations fully and will take appropriate action.  Any company, or individual that participates in any of the above prohibited conduct, will have its actions reported to the appropriate authorities, will be investigated fully, will have its offer rejected and/or contract terminated, and will not be eligible for future contracts with Mercy Corps. Employees participating in such conduct will have his/her employment terminated.

Violations will also be reported to Mercy Corps’ donors, who may also choose to investigate and debar or suspend companies and their owners from receiving any contract that is funded in part by the donor, whether the contract is with Mercy Corps or any other entity.

2.2 	Tender Basis:

- All offers shall be made in accordance with these instructions, and all documents requested should be furnished, including any required (but not limited to) supplier-specific information, technical specifications, drawings, bill of quantities, and/or delivery schedule. If any requested document is not furnished, a reason should be given for its omission in an exception sheet.

- No respondent should add, omit or change any item, term or condition herein.

- If suppliers have any additional requests and conditions, these shall be stipulated in an exception sheet.

- Each bidder may make one response only.

- Each offer shall be valid for the period of [90 days] from its date of submission.

- All offers should indicate whether they include taxes, compulsory payments, levies and/or duties, including VAT, if applicable.

- Suppliers should ensure that financial offers are devoid of calculation errors. If errors are identified during the evaluation process, the unit price will prevail. If there is ambiguity on the unit price, the Selection Committee may decide to disqualify the offer.

- Any requests for clarifications regarding the project that are not addressed in written documents must be presented to Mercy Corps in writing. The answer to any question raised in writing by any bidder will be issued to that bidder. In some cases Mercy Corps may choose to issue clarifications to all bidders. It is a condition of this tender that no clarification shall be deemed to supersede, contradict, add to or detract from the conditions hereof, unless made in writing as an Addendum to Tender and signed by Mercy Corps or its designated representative.

- This Tender does not obligate Mercy Corps to execute a contract nor does it commit Mercy Corps to pay any costs incurred in the preparation and submission of bids. Furthermore, Mercy Corps reserves the right to reject any and all offers, if such action is considered to be in the best interest of Mercy Corps.

2.3 	Supplier Eligibility

Suppliers may not apply, and will be rejected as ineligible, if they :

- Are not registered companies

- Are bankrupt or in the process of going bankrupt

- Have been  convicted of illegal/corrupt activities, and/or unprofessional conduct

- Have been guilty of grave professional misconduct

- Have not fulfilled obligations related to payment of social security and taxes

- Are guilty of serious misinterpretation in supplying information

- Are in violation of the policies outlined in Mercy Corps Anti Bribery or Anti-Corruption Statement

- Supplier (or supplier’s principals) are on any list of sanctioned parties issued by; or are presently excluded or disqualified from participation in this transaction by: the United States Government or United Nations by the United States Government, the United Kingdom, the European Union, the United Nations, other national governments, or public international organizations.

Additional eligibility criteria, if applicable, are stated in section 3.2 of this tender.

2.4   	Response Documents

Bidders must submit an offer in their own format and ensure it contains all the required documents and information specified in this tender. bidder

2.5	Acceptance of Successful Response

Documentation submitted by bidders will be verified by Mercy Corps. The winning bidder will be required to sign a contract for the stated, agreed upon amount.

2.6	Anti-Terrorism

It is Mercy Corps’ policy to comply with humanitarian principles and the laws and regulations of the United States, the European Union, the United Nations, the United Kingdom, host nations, and other applicable donors concerning transactions with or support to individuals or entities that have engaged in fraud, waste, abuse, human trafficking, corruption, or terrorist activity. These laws and regulations prohibit Mercy Corps from transacting with or providing support to any individuals or entities that are the subject of government sanctions, donor rules, or laws prohibiting transactions or support to such parties.

# Criteria & Submittals

3.1 Contract Terms Mercy Corps intends to issue a [Fixed Price] contract to one or several companies or organization(s). The successful bidder(s) shall be required to adhere to the statement of work and terms and conditions of the resulting contract. The anticipated contract is incorporated in Section 6 herein. By submitting a bid, bidders certify that they understand and agree to all of the terms and clauses contained in Section 6.

3.2 RFB Submittals Documents and required information listed in tender submittals are necessary in order to support the eligibility criteria and to conduct evaluations of received offers (and due diligence). While absence of these documents and/or information does not denote mandatory disqualification of suppliers, the lack of these items has the potential to severely and negatively impact the evaluation of an offer. Documents supporting the Eligibility Criteria: - Legal Status: Must be a legally registered and licensed construction company in Sudan or any other eligible country with valid registration documents. - Relevant Experience: Must have successfully completed a minimum of three (3) water point rehabilitation or small-scale civil/mechanical water infrastructure projects of a similar scope (e.g., hand pumps, water yard rehabilitation) in Sudan in the last five years. - Financial Capacity: Must demonstrate adequate financial resources, with an average annual turnover of at least USD 15,000 (or equivalent in SDG) over the last three years from 1st January 2020 (attach bank statements). Documents to conduct the Evaluation and additional Due Diligence: - Complete company profile including organogram - Relevant Experience: Previous contracts / orders / completion certificates - Financial Capacity: Bank statement for the last 3 years from 1st January 2020 - No Conflict of Interest: Must confirm that no staff member or director is related to or employed by Mercy Corps. - Technical Capacity: Must confirm immediate access to or ownership of the equipment listed in Section 4.B. Price Offer: The Price offer is used to determine which offer represents the best value and serves as a basis of negotiation before award of a contract. As a Fixed-Price contract, the price of the contract to be awarded will be an all-inclusive fixed price basis, either in the form of a total fixed price or a per-unit/deliverable fixed price. No profit, fees, taxes, or additional costs can be added after contract signing. Bidders must show unit prices, quantities, and total price. All items must be clearly labeled and included in the total price offered. Bidders must include VAT and customs duties in their offer The following information in the order listed must be included in the bid of any potential bidder: - Cover Letter explaining interest to be a contracted vendor or supplier. The content of the cover letter shall include the following information: - A detailed specification of the offered goods, services and/or works - Warranty (if necessary and appropriate) - Delivery time - Price validity date (for this purpose and as stated on the advertisement, quote given shall remain unchanged for 180 working days) - A Price Offer detailing the unit price only - Completed and signed Mercy Corps Supplier Information Form (template provided in section 7) - Other important documents the bidder feels need to be attached to support their bid The original bid shall be signed by the bidder or a person or persons duly authorized to bind the bidder to the contract. Financial offer pages of the bid shall be initialized by the person or persons signing the bid and stamped with the company seal. Any interlineations, erasures, or overwriting shall be valid only if they are initialized by the person or persons signing the bid.

3.3 Currency Offers should be submitted in: UNITED STATES DOLLARS Payments will be made in: UNITED STATES DOLLARS

3.4 Evaluation Lowest Price, Technically Acceptable (LPTA) Mercy Corps Tender Committee will conduct an evaluation which will grade selection criteria on a pass/fail basis. Supplier’s bids must meet the minimum standard established here in order to be reviewed on technical criteria. Any bidder who receives a failing mark on any criteria will be automatically disqualified from the tender process. The lowest price bid(s) will be accepted as the winning bidder(s) assuming the price is deemed fair and reasonable and subject to the additional due diligence. Bidder pass/fail criteria are as follows: Selection Criteria; Pass or Fail. Legal Status: Must be a legally registered and licensed construction company in Sudan or any other eligible country with valid registration documents.. Relevant Experience: Must have successfully completed a minimum of three (3) water point rehabilitation or small-scale civil/mechanical water infrastructure projects of a similar scope (e.g., hand pumps, water yard rehabilitation) in Sudan in the last five years.. Financial Capacity: Must demonstrate adequate financial resources, with an average annual turnover of at least USD 15,000 (or equivalent in SDG) over the last three years from 1st January 2020 (attach bank statements)..

3.4.1 Additional Due Diligence Upon completion of both the evaluations Mercy Corps may choose to engage in additional due diligence processes with a particular bidder or bidder(s). The purpose of these processes is to ensure that Mercy Corps engages with reputable, ethical, responsible Suppliers with solid financials and the ability to fulfill the contract. Additional due diligence may take the form of the following processes (though it is not limited to): - Reference Checks - Supplier’s facility visits - Analysis of validated bank statements - Review of personnel profiles and qualifications - Review of Company Profile - Current or previous orders for similar supplies of related values delivered (Min 3 Required) - Key Personnel CVs, 3-page max per personnel - ICC check through Mercy Corps internal system - Detailed goods / Service delivery specifications

# Scope of Work/Technical Specifications

4.1 Background

Mercy Corps is interested in receiving a detailed bid from Contractors for the rehabilitation of hand pumps and water yard in Alrahad Locality. The work covers civil, mechanical, and electrical components necessary to restore water points to full operational capacity, ensuring safe and sustainable water access for the community.

As a result, Mercy Corps is seeking a contractor to provide the below listed water supply repair and rehabilitation services:

- Hand Pumps (2 sites):

  - Alshamam Hand Pump (BoQ 2)

  - Makankana Hand Pump (BoQ 3)

- Water Yard (1 site):

  - Wad Abakar Water Yard (BoQ 4)

## Preliminaries, Safety, and Site Management (BoQ 0)

- Site Preparation: Clearing of all rubbish, bushes, and obstacles to ensure safe access for construction workers.

- Site Establishment: Provision of adequate temporary electrical and water supply, including generators, cables, pumps, and storage tanks.

- Safety & OSH: Installation of safety signage, provision of Personal Protective Equipment (PPE), and compliance with Occupational Safety and Health (OSH) requirements.

- Site Infrastructure: Establishment of sign boards, temporary material storage, site offices, and separate sanitary facilities for men and women.

- Closeout: Thorough cleaning of the entire project site and removal of all residual materials prior to handover.

## B. Typical Civil Works (Hand Pumps) (BoQ 1)

- Demolition and removal of existing concrete floors and drainage lines.

- Excavation, disposal of materials off-site, and backfilling with selected fill material.

- Supply and casting of reinforced concrete floor slabs and collection pits.

- Construction of U-shaped water drainage channels with proper slope and curing.

## C. Hand Pump Rehabilitation (BoQ 2, 3)

- Supply and installation of riser pipes, hand pump rods, and complete cylinder assemblies.

- Supply and installation of manual pump basins and complete manual pump heads.

## D. Water Yard Rehabilitation (BoQ 4)

- Supply and installation of riser pipes, submersible pumps, and control panels.

- Supply and installation of electrical cables and connections.

- Construction of perimeter fencing and access gates.

# 4. PROJECT MANAGEMENT REQUIREMENTS

## A. Standards, Supervision, and Documentation

- Material Quality: All construction materials must be approved by the Supervising Engineer and match agreed specifications.

- Workmanship & Compliance: All works must comply with approved Technical Specifications and instructions.

- Inspection & Approval: All phases must be approved by the Supervising Engineer before proceeding.

- Pricing: Prices cover all additional materials, labor, or associated costs.

- Site Visit: Contractors are strongly advised to visit sites prior to bidding.

## B. Site Equipment and Plant List

The Contractor must demonstrate access to the following minimum equipment:

| Equipment Name | Minimum Quantity | Purpose |
| --- | --- | --- |
| Concrete Mixer | 1 | For all foundation and RC slab pouring |
| Compacters (Plate/Roller) | 1 | For compacting backfill material |
| Welding Machine | 1 | For fabrication and assembly |
| Submersible Pump Installation Tools | 1 | For pump installation/retrieval |
| General Hand Tool Sets | 2 | Measuring, cutting, plumbing, electrical |
| Transport Vehicle | 1 | Material delivery and personnel mobilization |

## C. Key Staffing and Qualifications

The Contractor must employ qualified personnel with the following minimum capacity:

| Staff Position | Minimum Quantity | Required Qualifications | Responsibility Overview |
| --- | --- | --- | --- |
| Project Manager | 1 | Bachelor’s degree in civil engineering, 5+ years’ experience | Overall project supervision and contract management |
| Site Engineer | 1 | Diploma/bachelor’s in civil engineering, 3+ years’ experience | Direct implementation and quality checks |
| Civil Foreman | 1 | Technical Certificate, 7+ years’ experience | Supervision of civil works |
| Mechanical Technician | 1 | Technical Diploma in Mechanics/Hydraulics | Pump installation and mechanical works |
| Health and Safety Officer | 1 | Certified in OSH, 3+ years’ experience | Site safety compliance and PPE distribution |

# PROJECT DELIVERABLES

The Contractor is responsible for the timely delivery of the following:

| Category | Deliverable Item | Quantity | Description |
| --- | --- | --- | --- |
| Physical Assets | Fully Operational Hand Pumps | 2 Sites | All civil, mechanical, and site works complete |
| Physical Assets | Fully Operational Water Yard | 1 Site | All civil, mechanical, and electrical systems complete |
| Physical Assets | Cleaned and Handed-Over Sites | 3 Sites | Removal of all construction debris and temporary structures |
| Technical Documentation | Shop Drawings | 1 Set | Submitted and approved prior to fabrication |
| Technical Documentation | As-Built Drawings | 1 Set (Soft & Hard Copy) | Final drawings reflecting exact specifications |
| Technical Documentation | Test Reports | 1 Set | Water quality and pump performance test results |
| Management & Safety | Daily/Weekly Photo Reports | Continuous | Digital photos showing progress |
| Management & Safety | Final Completion Report | 1 | Comprehensive narrative report |
| Management & Safety | Handover Certificate | 1 | Signed document confirming project completion |

# 7. ENVIRONMENTAL, SOCIAL SAFEGUARDS (ESS) & SAFETY CONSIDERATIONS

The Contractor is strictly responsible for adhering to all ESS and safety requirements below. Non-compliance may result in contract termination. The ESS requirements/considerations will apply at each of the listed Lots.

- The contractors and all their employees must sign the Mercy Corps’ Do No Harm policy.

- The contractor must have a Code of Conduct and ensure all staff hired for the contract have been trained on, and a code of conduct signed.

- Compliance with Mercy Corps' Environmental and Social Management Framework (ESMF) and ensure zero harm to participants and the community during the life of the contract.

- Each of the lots must have a site specific Environmental and Social Management Plan (ESMP) produced by the contractor and reviewed by the Mercy Corps ESS team.

- Track, Implement and periodically report against mitigation measures for all the identified E&S risks.

- The contractor and workers must attend mandatory ESS induction training upon signing the contract, prior to commencement of the contracted works. The training will be facilitated by Mercy Corps which includes PSEA (Protection from Sexual Exploitation and Abuse), Sexual Exploitation & Abuse, Sexual Harassment, child protection, and child labor.

- The contractors must ensure efficient resources utilization, prevent any form of pollution from machinery & vehicles, and sustainably manage all forms of waste (hazardous & non-hazardous) generated during the period of the contract with the Mercy Corps and at decommissioning of camping sites.

- Avoid cutting trees without prior approval from the relevant government authorities in the operational area(s)/lots.

- Contractors must establish a functional/culturally appropriate Grievance Redress Mechanism for their workers to report work-place complaints/concerns.

- Ensure provision of Personnel Protective Equipment (PPE) and enforce mandatory & appropriate use of the PPE.

- Ensure community safety from moving equipment through road safety signage in appropriate local language.

- Report any incident/accidents or near miss to Mercy Corps within 24 hours.

# 8. CONTRACT DURATION AND PROJECT TIMELINE

The total contract duration for all works is 12 weeks. The Contractor shall submit a detailed work plan showing timelines for each site for approval by the Supervising Engineer.

# 9. PAYMENT SCHEDULE AND MILESTONES

Payments will be processed based on the completion and verification of the following milestones:

| Milestone | Description | Gross Percentage | Net Payout Percentage | Mandatory Verification Checklist |
| --- | --- | --- | --- | --- |
| Milestone 1: Preliminaries & Civil Start | Completion of all Preliminaries (BoQ 0) and Civil Works (BoQ 1) on 50% of Hand Pump sites (1 site). | 20% | 18% | Site fully mobilized. All demolition, excavation, and RC floors approved for 1 Hand Pump. |
| Milestone 2: Mechanical & Intermediate Completion | Completion of all Civil Works (BoQ 1) on all Hand Pump sites. Complete Mechanical Installation on all Hand Pumps (BoQ 2, 3). | 40% | 36% | Final inspection of all Hand Pumps. Water Yard foundations complete. |
| Milestone 3: Final Completion | Completion of Water Yard (BoQ 4) including pumping tests, pump installation, fencing, and full functionality. Final cleaning, As-Built Drawings, and Submission of all test/photo reports. | 40% | 36% | Final commissioning and water quality test passed at Water Yard. All Hand Pumps fully operational. Final Handover Certificate signed. |
| Milestone 4: Defects Liability / Retention Release | Release of the remaining 10% retention amount upon the successful expiry of the specified Defects Liability Period (DLP), typically 6 to 12 months after Milestone 3. | N/A | 10% (The final payment) | Final joint inspection conducted after the DLP, confirming all works are defect-free and the facilities remain fully operational. Defects Liability Certificate signed by the Engineer. |

# 10. BILL OF QUANTITIES

## General Notes:

- All the works are in accordance with approved Technical Specification and the instructions of the Supervising Engineer or proxy for these construction works.

- All construction materials should be approved in accordance with the agreed upon service requests, task/works specifications, and equipment used in transport of materials is operated in compliance with the manufacturers operational parameters.

- All the items include provision of all necessary materials and installation/commissioning-related works.

- All phases of work should be approved by the Supervising Engineer before moving to next phase of the work schedule.

- Awareness-raising posters regarding safety on site shall be displayed throughout the construction site.

- Technical and construction-related questions as well as addressing any quality issues related to expected works are to be directed to the Supervising Engineer for resolution; and final technical decision.

- Supervising Engineer and Mercy Corps require regular photo report of work conducted to date. These photo reports will be used to track progress against the agreed upon Scope of Work and Bill of Quantities documents for the project.

- Shop Drawings: The Contractor shall provide at any time before commencement or during the progress of the work shop drawings as directed by the Supervising Engineer. Shop drawings should also be provided for activities related with assembly such as water tank installation, solar system installation, and generator anchoring.

- As-Built Drawings: The Contractor shall carry out the correction of all prints of Drawings including the preparation on completion of the Works. One softcopy (CD or DVD) and one color printed of As-Built Drawings.

- Samples: The Contractor shall allow for providing and submitting to the Supervising Engineer as he may require, samples of all materials and goods which the Contractor proposes to incorporate into the works.

- Site Visit: All Contractors/bidders are strongly advised to visit the proposed sites prior to pricing and submitting bid offers. Contractors/bidders shall coordinate with the Mercy Corps and Supervising Engineer to obtain information about the locations/coordinates of the proposed sites and arrange at their own costs site visits to determine the conditions of the water boreholes facilitates, rehabilitation needed, material storage area and material delivery arrangements. Contractors/bidders are solely responsible for that and no price increase shall be made later on during the project period in case of their failure of doing so.

- Complete Project Price: This BOQ is part of the complete project documents (drawings, BOQ, and materials specifications and notes on pricing) and must be read together. Any discrepancies between these documents shall be brought to the immediate attention of the Supervising Engineer. Prices given by the contractor on this BOQ are to cover any and all additional materials, labor or associated costs to complete the works as documented on the complete project documents.

## BoQ 0: Preliminaries

| Item | Description | Unit | Qty | Unit Rate | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Preliminaries / Site Prep |  |  |  |  |
| 1.1 | Site Preparation: This site will need to be cleared of all rubbish, bushes, and materials. Remove any obstacles to the safe access of construction workers is also to be planned for; including any buried materials that will interfere with the establishment of the various civil works. All initial site preparation, clean-up and removal of materials to be conducted to the instructions of the site manager and the approval of the Supervising Engineer. | Lump Sum | 1 |  |  |
| 1.2 | Electrical, Water supply and Running cost: The Contractor shall establish and commission an adequate temporary electrical and water supply for the works, suitable for all purposes, until handing over and shall pay all charges for all electrical and water consumption. Including any necessary cables, generators, MDBs, water pumps, water storage tanks, distribution pipe network, etc. required for the execution of the works. Running costs, price includes; Power & services, water, documents, photos, records, and Client meetings on site. | Lump Sum | 1 |  |  |
| 1.3 | Sign Boards: The Contractor shall establish and maintain One (1) sign boards for the Site (1.5 m width X 2m height), total height of sign board is 3 m, consisting of painted galvanized steel board plate, steel tubular section, steel angles, all painted with two coats white oil paint back and front and supported above the ground with steel framing and struts painted matt black and set into the ground and fixed in concrete foundation size (10 x 10 x 10). The sign board shall be lettered by a skilled sign writer in Arabic and English and shall include: The Project details, specific mention of the THABAT AF1 project's stakeholders as per the approved design by Mercy corps. Large scale layouts are to be submitted to the Supervising Engineer for approval before manufacture. No advertising material other than this will be permitted. No other sign boards or advertisements on or around the site will be permitted unless approved by the Supervising Engineer. | Lump Sum | 3 |  |  |
| 1.4 | Cleaning the Works: Immediately prior to handing over the Works the Contractor shall thoroughly clean all project site area, remove material and generally keep the area ready for operation and use all to the approval of the Supervising Engineer. | Lump Sum | 1 |  |  |
| 1.4 | Temporary Sanitary Facilities: The contractor shall establish basic worksite services including all temporary separate sanitary facilities for men and women that are sufficient in number and conveniently and safely located (mobile sanitary facilities could be considered). | Lump Sum | 1 |  |  |
| 1.5 | PPE & OSH: The contractor should design and install all worksite safety and personal protective equipment requirements signage. In addition to all work and occupational safety signs all around the site. Safety and Health provision, traffic barriers at site limit, safety gears for all laborers, proper tools and PPEs (including COVID-19 prevention measures). Safety equipment, hazard & traffic management, safe-working requirements, health/safety records & analysis, supervision & training, induction, protective clothing; & the like; Site bins and cleaning. | Lump Sum | 1 |  |  |
| 1.6 | Insurance payment: The contractor should provide and pay for accident and liability: workman’s compensation, Liability insurance and third party. This amount will be paid to the contractor upon submission of payment receipt to the relevant authorities. | Lump Sum | 1 |  |  |
| 1.7 | Materials Storage and Site office: The Contractor shall provide and maintain temporary storage and site office made of zinc sheets and steel pipes fixed on reinforced concrete slab and use it as materials storage (cement and other perishable materials and the like) and site office for regular meetings. Contractors should also provide chairs and tables for regular site meetings. | Lump Sum | 1 |  |  |
|  | TOTAL FOR ALL SECTIONS (USD) |  |  |  |  |
|  | VAT 17% |  |  |  |  |
|  | GRAND TOTAL for BoQ 0 |  |  |  |  |

## BoQ 1: Typical Hand Pump Civil works

| Item | Work Description | Unit | Quantity | Unit Price | Total Cost |
| --- | --- | --- | --- | --- | --- |
| 1 | Demolition and removal of existing concrete floor (1.8m diameter, 20cm thick) and disposal off-site | m² | 3 |  |  |
| 2 | Ditto, but for water drainage line (3.5m long, 30cm wide) | m.l | 3.5 |  |  |
| 3 | Excavation to a depth of 50cm and disposal off-site | m³ | 8 |  |  |
| 4 | Supply and fill with selected fill material (Reqaita) in two layers, 50cm total depth, with proper watering and compaction | m³ | 8 |  |  |
| 5 | Supply and cast reinforced concrete floor (circular, 1.8m diameter), using 12mm @150mm c/c in both directions, mix 1:2:4, the floor is 15cm thick, cured for 5 days | m³ | 0.4 |  |  |
| 6 | Ditto, but for collection pit (1m x 1m), 15cm thick | m³ | 0.15 |  |  |
| 7 | Supply and construct U-shape Sectioned water drainage channel (3.5m long, 30cm wide, 10cm thick with 5cm raised sides) using plain concrete mix 1:3:6, including proper slope, plastering, and 5-day curing | m³ | 0.8 |  |  |
|  | Total |  |  |  |  |
|  | 17% VAT |  |  |  |  |
|  | GRAND TOTAL for BoQ 1 |  |  |  |  |

## BoQ 2: Rehabilitation of Alshamam Hand Pump- Alrahad Locality

| Item No. | Description | Unit | Quantity | Unit Rate | Total Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Conduct water quality testing | L.S | 1 |  |  |
| 2 | Supply and installation of 11 pieces of 1¼" Indian-made riser pipes, each 3 meters long | No | 11 |  |  |
| 3 | Supply and installation of 11 hand pump rods | Operation | 11 |  |  |
| 4 | Supply and installation of 1 complete cylinder | Operation | 1 |  |  |
| 5 | Supply and installation of 1 manual pump basin | Operation | 1 |  |  |
| 6 | Supply and installation of 1 complete manual pump head | Operation | 1 |  |  |
|  | Total |  |  |  |  |
|  | 17% VAT |  |  |  |  |
|  | GRAND TOTAL for BoQ 2 |  |  |  |  |

## BoQ 3: Rehabilitation of Makankana Hand Pump- Alrahad Locality

| Item No. | Description | Unit | Quantity | Unit Rate | Total Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Conduct water quality testing | L.S | 1 |  |  |
| 2 | Supply and installation of 10 pieces of 1¼" Indian-made riser pipes, each 3 meters long | No | 10 |  |  |
| 3 | Supply and installation of 10 hand pump rods | Operation | 10 |  |  |
| 4 | Supply and installation of 1 complete cylinder | Operation | 1 |  |  |
| 5 | Supply and installation of 1 manual pump basin | Operation | 1 |  |  |
| 6 | Supply and installation of 1 complete manual pump head | Operation | 1 |  |  |
|  | Total |  |  |  |  |
|  | 17% VAT |  |  |  |  |
|  | GRAND TOTAL for BoQ 3 |  |  |  |  |

## BoQ 4: Rehabilitation of Wad Abakar Water Yard- Alrahad Locality

| Item No. | Description | Unit | Quantity | Unit Rate | Total Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | Well production test / Conduct water quality testing Execution of constant-rate pumping test | L.S | 1 |  |  |
| 2 | Supply and installation of 12 Indian-made pipes, 1.25 inches in diameter and 3 meters long, including a half-clamp and a well cap, as directed by the supervising engineer. | No. | 12 |  |  |
| 3 | Supply and installation of a European-made, 1.25-inch electric submersible pump. The pump's impellers are made of rust-resistant steel. Its output is 3 to 5 cubic meters with a vertical lift of 60-75 meters. The pump comes with all its accessories, including a control panel, a changeover switch, and an electrode cable, as directed by the supervising engineer. | Job | 1 |  |  |
| 4 | Supply and installation of a 6 mm, 3-wire flat borehole cable, as directed by the supervising engineer. | ML | 50 |  |  |
| 5 | Removal of the old fence and supply of materials and construction of a new fence from 5 mm wire mesh with 5x5 cm openings. Dimensions: 20x20 meters. Specifications: imported angle iron posts (3-inch, 5 mm in the corners and 2-inch, 5 mm at 200 cm intervals). Holes are 40x40x60 cm. The fence height is 150 cm above ground. The angles are secured with four horizontal lines of 12 mm standard rebar and a 1:3:6 concrete mix. The posts will be thoroughly watered. | ML | 80 |  |  |
| 6 | Supply and installation of 5 m³ plastic water tank (Tiga brand), including inlet and outlet piping using 1" galvanized pipes, brass ball valve (1"), all necessary water connections, and mounting on a steel frame made of 1½" angle iron and 1¼" flat bars, painted white — as per supervising engineer’s instructions | No | 1 |  |  |
| 7 | Supply and installation of double-leaf gate (total width 350 cm), frame of 2"×5 mm imported angle, infill of 10 mm steel bars spaced 20 cm horizontally and vertically, 3"×5 mm angle posts fixed in 50×50×70 cm concrete base, gate ramp, appropriate painting | Job | 1 |  |  |
| 8 | Supply and Installation of Large Distribution System: Provide materials and install one 2" galvanized standpipe with a 2" brass ball valve and 8m long 2" hose nozzle, including all necessary operational and control connections. Supply materials and construct a kiosk using 2-inch, 5mm thick angle bars and 35-gauge zinc panels, with expanded metal walls (dimensions: 2m x 2m x 2.5m). The kiosk includes a zinc roof, expanded metal side walls, a single-panel door, concrete flooring, and painting per specifications and supervising engineer’s instructions | L.S | 1 |  |  |
| 9 | Construction of the distribution point with dimensions (200×70×50 cm) and flooring (3×3 m). Supply and installation of 6 brass taps, ¾", with all necessary connections as per engineer’s directions. | L.S | 1 |  |  |
|  | Total |  |  |  |  |
|  | 17% VAT |  |  |  |  |
|  | GRAND TOTAL for BoQ 4 |  |  |  |  |

## Total Financial Offer for Work Package

| BoQ No. | BoQ Name | Frequency | BoQ Amount | Total Amount |
| --- | --- | --- | --- | --- |
| 0 | BoQ 0: Preliminaries | 1 |  |  |
| 1 | BoQ 1: Typical Civil Work for Hand Pumps | 2 |  |  |
| 2 | BoQ 2: Rehabilitation of Alshamam Hand Pump | 1 |  |  |
| 3 | BoQ 3: Rehabilitation of Makankana Hand Pump | 1 |  |  |
| 4 | BoQ 4: Rehabilitation of Wad Abakar Water Yard | 1 |  |  |
|  | Total Financial Offer |  |  |  |

# Sample Contract

This is the anticipated contract. However, if required, additional terms and conditions may be added by Mercy Corps in the final contract. (Not attached)

[Insert Sample Contract]

# Attachments to the RFQ

Attachment 1 -Supplier Information Form template

Attachment 2 -Price offer/ BOQ template

Attachment 3 – SOW

Attachment 4 –Beneficial Ownership Disclosure Form